## Overview
BUS 9430: Business Analytics Project Management
Project Plan Development homework (10 pts)
Prepared by | Raúl J. Solá Navarro
Course / Section | BUS 9430, Fall 2026, Prof. Joseph Sommer
Date prepared | 09/26/2026
Last updated | 10/05/2026
Project title | Day-Ahead Solar Output Forecasting for Grid Stability (CAISO)
Business problem | CAISO, California's grid operator, commits power plants and reserves the day before it needs them. If the solar forecast runs too high, operators face last-minute purchases or plant starts. If it runs too low, they hold reserves they never use, and in spring they curtail solar that the grid cannot absorb. A better day-ahead forecast reduces both costs.
Analytics objective | Build and evaluate a day-ahead forecast of CAISO utility-scale solar generation (MW, hourly). Benchmark it against a persistence baseline and CAISO's own day-ahead forecast, then translate the remaining error into an estimate of the reserve capacity (MW) operators would need to hold.
Success measures | (1) Normalized MAE (percent of installed solar capacity, daylight hours) no more than 1.25 times CAISO's own day-ahead error. (2) RMSE skill score of at least 0.30 versus persistence. (3) P95 overshoot at least 20% below the persistence baseline. (4) MAPE reported on hours above 5% of capacity, not used to rank models. (5) A one-page plain-language readout. These targets are starting points and get rechecked once the baseline exists (Task 11).
Scope / boundaries | CAISO balancing authority, utility-scale solar only. Hourly forecasts issued the day before. Data from January 2024 to the latest available month. Out of scope: wind and other grid operators, intraday updates, plant-level forecasts, and dispatch or production-cost modeling.
Primary data sources | EIA Open Data API, hourly solar generation (eia.gov/opendata). CAISO OASIS, day-ahead solar forecast report SLD_REN_FCST (oasis.caiso.com). Open-Meteo Previous Runs API, weather forecasts issued 24 hours earlier (open-meteo.com/en/docs/previous-runs-api). NLR NSRDB, clear-sky and observed irradiance (developer.nlr.gov/docs/solar/nsrdb). EIA Form 860M, installed capacity. CAISO Production and Curtailments Data, curtailed hours. Backup for code testing only: Kaggle plant-level solar data.
Key limitations (stated up front) | The weather-forecast archive starts in January 2024, so history is about two and three-quarter years. Generation data is reported after curtailment, so spring output understates what the sun could have supplied. I flag curtailed hours and report results with and without them. CAISO stopped publishing its curtailment report on June 1, 2025, so 2026 curtailment data needs a different source.
Framework | This plan follows CRISP-DM (Business Understanding, Data Understanding, Data Preparation, Modeling, Evaluation, Deployment), shown here as the Workstream column.
Course milestones this plan is built around | Capstone 1 (Issue Selection and Plan): Oct 13 ¦ Capstone 2 (Data Understanding and Preparation): Nov 16 ¦ Capstone 3 (Models and Results): Dec 14
Supporting documents | Task 1: Problem Statement and Success Metrics memo. Task 2: Data Source List and Access Plan.

## Project Plan
Task # | Task Name | Task Description | Workstream | Owner / Role Responsible | Start Date | End Date | Duration (Days) | Dependency | Milestone (Y/N) | Key Deliverable | Status
1 | Define project scope and success metrics | Confirm the business problem (day-ahead solar forecasting for CAISO grid stability), define the target variable, and set success metrics (nMAE versus CAISO's forecast, skill score versus persistence, P95 overshoot). | Business Understanding | Raul (with team input) | 2026-09-26 | 2026-09-29 | 4 | None | No | Problem statement and success-metrics memo | In Progress
2 | Identify and shortlist data sources | Research and select data sources: EIA hourly generation, CAISO's day-ahead forecast, Open-Meteo 24-hour-ahead weather forecasts, NSRDB irradiance, and EIA-860M capacity. Confirm access requirements. | Business Understanding | Raul | 2026-09-29 | 2026-10-01 | 3 | 1 | No | Data source list and access plan | In Progress
3 | Draft and rehearse Capstone 1 presentation | Prepare slides covering the project issue, plan, target benefits, and delivery risks for the team's graded presentation. | Business Understanding | Team | 2026-10-01 | 2026-10-10 | 10 | 2 | No | Capstone 1 slide deck | Not Started
4 | Capstone 1: Issue Selection and Plan | Present the selected issue, project plan, target benefits, and delivery risks to the class (20% of course grade). | Business Understanding | Team | 2026-10-13 | 2026-10-13 | 1 | 3 | Yes | Graded presentation | Not Started
5 | Acquire generation and weather data | Register for EIA and NLR API access and pull January 2024 to the latest month of hourly CAISO solar generation, CAISO's day-ahead forecast, and 24-hour-ahead weather forecasts for several California points. | Data Understanding | Raul | 2026-10-14 | 2026-10-20 | 7 | 4 | No | Raw data extracts (EIA, CAISO, weather) | Not Started
6 | Profile data quality | Assess the data for gaps, outliers, curtailed hours, and timezone or unit differences between sources (standardize on UTC). | Data Understanding | Raul | 2026-10-20 | 2026-10-23 | 4 | 5 | No | Data quality report | Not Started
7 | Merge data and engineer features | Combine generation, weather, and capacity data into one hourly table; create features such as lagged generation, clear-sky index, forecast cloud cover and radiation, and seasonality indicators. | Data Preparation | Raul | 2026-10-23 | 2026-10-28 | 6 | 6 | No | Analysis-ready dataset | Not Started
8 | Create train / validation / test splits | Partition the dataset in time order (not randomly), holding out the most recent months for testing, to preserve time-series integrity. | Data Preparation | Raul | 2026-10-28 | 2026-10-30 | 3 | 7 | No | Split dataset | Not Started
9 | Prepare Capstone 2 materials | Summarize data profiling results and the quality/privacy assessment for the team's second graded presentation. | Data Preparation | Team | 2026-10-30 | 2026-11-13 | 15 | 8 | No | Capstone 2 slide deck | Not Started
10 | Capstone 2: Data Understanding and Preparation | Present data profiling, preparation approach, and quality/privacy assessment to the class (20% of course grade). | Data Preparation | Team | 2026-11-16 | 2026-11-16 | 1 | 9 | Yes | Graded presentation | Not Started
11 | Build and validate forecasting models | Build a persistence baseline plus candidate regression and tree-based models; tune and cross-validate in time order. | Modeling | Raul | 2026-11-17 | 2026-11-27 | 11 | 10 | No | Trained and validated models | Not Started
12 | Evaluate model performance | Compare nMAE, skill score, and P95 overshoot against persistence and CAISO's own forecast, and translate forecast error into reserve (MW) implications for the grid. | Evaluation | Raul | 2026-11-30 | 2026-12-04 | 5 | 11 | No | Evaluation summary | Not Started
13 | Build performance visualizations | Create charts comparing actual versus predicted output and forecast error by month for the final report. | Evaluation | Raul | 2026-12-04 | 2026-12-08 | 5 | 12 | No | Performance charts | Not Started
14 | Prepare and rehearse Capstone 3 presentation | Assemble final findings, limitations, and recommendations into the team's closing presentation. | Deployment | Team | 2026-12-08 | 2026-12-12 | 5 | 13 | No | Capstone 3 slide deck | Not Started
15 | Capstone 3: Final Presentation | Present final models, results, and recommendations to the class (20% of course grade). | Deployment | Team | 2026-12-14 | 2026-12-14 | 1 | 14 | Yes | Graded final presentation | Not Started
Legend:
Shaded rows | Milestone (graded course deliverable)
Status column | Dropdown; edit as the project progresses. Colors update automatically.

## Risk Register
# | Risk | Related Task # | Likelihood | Impact | Mitigation
1 | EIA or NLR API access delays or rate limits slow the data pull | 5 | Low | Medium | Request both API keys by Oct 7, before Capstone 1. If the EIA key is late, use the ACTUAL values from the CAISO OASIS report as the target.
2 | Timestamp zones differ across sources (UTC, GMT, local time) | 6, 7 | Medium | High | Set UTC as the project standard and check against known sunrise and sunset times before moving on.
3 | Weather-forecast archive starts January 2024, so history is about two and three-quarter years | 5, 8, 11 | High | Medium | Hold out recent months in time order, report error by month, and state plainly that each calendar month appears only two to three times.
4 | Model overfits a short history | 11 | Medium | Medium | Start with simple baselines, use chronological splits, and cross-validate in time order.
5 | Solar output is reported after curtailment, so spring actuals understate what the sun could supply | 6, 12 | High | Medium | Flag curtailed hours using CAISO's curtailment files (through December 2025) and report results with and without them. Confirm what replaces the report for 2026.
6 | Competing coursework deadlines (Quiz 1 Oct 26, Quiz 2 Nov 30) land inside feature building and evaluation | 7, 12 | High | Low-Medium | Finish the feature work ahead of Quiz 1 and start evaluation prep before Quiz 2. Keep buffer days ahead of each capstone.
7 | Team disagrees on scope after work has started | 1, 2 | Low | High | Lock the scope with the team by Oct 8 (memo sign-off) before any data work begins.